## Instructions
ITC327W Project Progress and Contribution Workbook
Use this workbook throughout the semester. Update it after each project phase and submit the same workbook again so that progress can be tracked over time.
Sheet | Purpose | Evidence and Accountability Rules
Project Overview | Enter the group and project details. The dashboard summarises task progress automatically. | 1 | Every student must be assigned meaningful work in Microsoft Project.
Task Progress | Record planned and completed tasks, responsible students, dates, status, percentage completed and evidence. | 2 | Completed work must be supported by evidence such as GitHub activity, meeting records, document sections, screenshots or stakeholder communication.
Individual Contributions | Record the work personally completed by each student. Every entry must have evidence. | 3 | GitHub commits are not the only evidence. Planning, interviewing, documentation, coordination and quality review also count.
Stakeholder Engagement | Record meetings, calls and emails with the stakeholder and the main outcomes. | 4 | Do not record work as completed by a student when it was completed by someone else.
Challenges & Actions | Record project challenges, their effect and the corrective action taken. | 5 | Do not place passwords, API keys, identity numbers, private contact details or confidential records in this workbook or on GitHub.
Phase Summary | Provide a short summary of the phase, including achievements, outstanding work and participation concerns. | 6 | The confidential individual peer evaluation must be completed separately on Blackboard.
Group Reflection | Complete one shared reflection after each phase. Be honest and specific.
Recommended Update Points
|  | Unit 1 / Phase 1 | Planning, stakeholder engagement, requirements and initial SRS
|  | Phase 2 | Architecture, UML, ERD and interface design
|  | Phase 3 | Development, integration, testing and demonstration
|  | Final | Overall project summary and final reflection

## Project Overview
Project Overview and Progress Dashboard
Project Information | Group Response | Task Status | Count
Group name or number | Bright Web Crafters | Completed | 30
Project title | School Portal System (School-Parental System) - ITC327W | In Progress | 0
Stakeholder or organisation | Reitzpark Primary School, Lenakeng High school, Thabong primary school | Not Started | 0
Group mentor |  | Delayed | 0
Reporting phase | Final | Blocked | 0
Reporting period |  | Overdue | 0
Overall status | Completed
Overall % complete | 100% | Contribution Summary | Count
Main achievement | Build our fully functional School Prental System | Contribution entries | 12
Main challenge | Being able to link our ASP.NET with supabase and flutter so that whatever that is upload on our ASP.NET application must appear on our flutter app e.g such as attendance that is marked on our ASP.NET must be visible on the flutter app | Verified entries | 12
Next planned activity | None | Unverified entries | 0
|  | Stakeholder engagements | 2

## Task Progress
Task Progress Tracker
Task ID | Reporting Phase | Activity | Task Description | Assigned Student(s) | Start Date | Due Date | Status | % Complete | Evidence / Link | Verified by Group | Lecturer Comment | Progress Flag
U1-01 | Unit 1 / Phase 1 | Activity 1.1 | Identify and confirm the external stakeholder | Group |  |  | Completed | 100 | Stakeholder interview forms signed by Reitzpark Primary School staff | Yes |  | Completed
U1-02 | Unit 1 / Phase 1 | Activity 1.1 | Document the current process and problem | Group |  |  | Completed | 100 | Problem Statement (SRS Sec. 1) and Current Process diagram (SRS Sec. 2.5.1) | Yes |  | Completed
U1-03 | Unit 1 / Phase 1 | Activity 1.1 | Define the project aim, objectives and scope | Group |  |  | Completed | 100 | SRS Sections 2.2-2.4 (Scope, Project Aim, Project Objectives) | Yes |  | Completed
U1-04 | Unit 1 / Phase 1 | Activity 1.2 | Prepare stakeholder interview questions | Group |  |  | Completed | 100 | Interview questionnaire used with Reitzpark Primary School staff | Yes |  | Completed
U1-05 | Unit 1 / Phase 1 | Activity 1.2 | Conduct and document the stakeholder interview | Group |  |  | Completed | 100 | 3 completed, signed interview forms from Reitzpark Primary School (Administrator, Educator, Remedial Education), school-stamped | Yes |  | Completed
U1-06 | Unit 1 / Phase 1 | Activity 1.3 | Compile the initial SRS | Group |  |  | Completed | 100 | BRIGHT_WEB_CRAFTERS_SRS.pdf (full SRS document, Sections 1-13) | Yes |  | Completed
U1-07 | Unit 1 / Phase 1 | Activity 1.3 | Create the initial Microsoft Project schedule | Group |  |  | Completed | 100 | Attached screenshots to our srs submission | Yes |  | Completed
U1-08 | Unit 1 / Phase 1 | Activity 1.3 | Create and configure the GitHub repository | Group |  |  | Completed | 100 |  | Yes |  | Completed
U1-09 | Unit 1 / Phase 1 | Activity 1.3 | Create the initial Supabase project | Group |  |  | Completed | 100 |  | Yes |  | Completed
U1-10 | Unit 1 / Phase 1 | Activity 1.3 | Complete the progress report and contribution record | Group |  |  | Completed | 100 | ITC327W_Project_Progress_Tracker_2026.xlsx (this workbook, being updated) | Yes |  | Completed
U1-11 | Unit 1 / Phase 1 | Activity 1.3 | Complete the Unit 1 group reflection | Group |  |  | Completed | 100 |  | Yes |  | Completed
U1-12 | Unit 1 / Phase 1 | Activity 2.1 | Evaluate technical, operational, economic, schedule and legal/ethical feasibility of the proposed project | Group |  |  | In Progress | 100 | SRS Sections 2.2.3 (Exclusions), 2.2.4 (Constraints) and 2.2.5 (Assumptions) already document scope, technical and schedule limits; formal feasibility study (technical/operational/economic/schedule/legal-ethical) still to be written up | Yes |  | On Track
U1-13 | Unit 1 / Phase 1 | Activity 2.2 | Identify, assess (likelihood and impact) and prioritise project risks; prepare a project risk register | Group |  |  | Completed | 100 | SRS Section 10 (Risk Analysis) identifies 6 risks - data breach/unauthorised access, multi-school data leakage, incorrect role enforcement, integration failures, network dependency, browser/device compatibility - each with mitigation and contingency plans; likelihood/impact ratings and formal risk register format still to be added | Yes |  | Completed
U1-14 | Unit 1 / Phase 1 | Activity 2.3 | Apply feasibility study and risk register findings: refine project scope, SRS requirements and update the Microsoft Project schedule | Group |  |  | Completed | 100 |  | Yes |  | Completed
U2-01 | Phase 2 | Activity 3.1 | Design the overall system architecture showing how the Flutter mobile app, ASP.NET Core Web API and Supabase backend work together as one integrated solution | Group |  |  | Completed | 100 | SRS Section 3.3 (System Environment) already defines the integration points - ASP.NET Core 8 Web API, Flutter mobile app, Supabase PostgreSQL/Auth/Storage; formal system architecture diagram still to be produced | Yes |  | Completed
U2-02 | Phase 2 | Activity 3.2 | Develop the use case diagram, sequence diagrams for key processes, and the Entity Relationship Diagram (ERD) with tables, fields, primary keys and relationships | Group |  |  | Completed | 100 | SRS Section 8 (Data Requirements) lists the 12 data entities, fields and relationships (Schools, Users, Students, Teachers, Classes, Enrollments, Attendance, Grades, Announcements, Announcement Recipients, Notifications, Events) as the basis for the ERD; use case diagram, sequence diagrams and the ERD itself still to be developed | Yes |  | Completed
U2-03 | Phase 2 | Activity 3.3 | Design the main Flutter mobile application and ASP.NET web application interfaces and assemble the complete system design baseline | Group |  |  | Completed | 100 | https://www.figma.com/proto/pG7mL3Oj2Rr37JAT9r7WJv/School-Parental-system?node-id=42-238&p=f&t=0WVSbhhXYOH6dG98-1&scaling=scale-down&content-scaling=fixed&page-id=0%3A1&starting-point-node-id=42%3A238, https://www.figma.com/proto/lPObV3qt8TfARP7lGBJZqU/School-Parental-System?node-id=197-2563&p=f&viewport=-167%2C288%2C0.1&t=Gi9OyypmECYmlsAf-1&scaling=contain&content-scaling=fixed&starting-point-node-id=197%3A2563&page-id=0%3A1, https://www.figma.com/proto/lPObV3qt8TfARP7lGBJZqU/School-Parental-System?node-id=224-463&p=f&viewport=-107%2C84%2C0.19&t=7iRvLo52rvJGZx2o-1&scaling=contain&content-scaling=fixed&page-id=218%3A2&starting-point-node-id=281%3A2266 | Yes |  | Completed
U3-01 | Phase 3 | Section 1 | Implement the shared Supabase backend from the approved ERD: required tables and fields (Schools, Users, Students, Teachers, Classes, Enrollments, Attendance, Grades, Announcements, Announcement Recipients, Notifications, Events) with primary keys, foreign keys and relationships | Group |  |  | Completed | 100 | Supabase project tables and schema script (GitHub backend setup folder); schema screenshots in SRS Implementation section |  |  | Completed
U3-02 | Phase 3 | Section 1 | Configure Supabase authentication, user roles and permissions (row-level access) as required by the approved SRS, and confirm Flutter and ASP.NET use the same Supabase project with demonstration data | Group |  |  | Completed | 100 | Supabase Auth/policy configuration screenshots (no keys shown); dummy demo records |  |  | Completed
U3-03 | Phase 3 | Section 2 | Develop the Flutter mobile application: main approved screens, navigation, forms and input validation based on the Figma mobile design | Group |  |  | Completed | 100 | Source code in mobile/ folder on GitHub; mobile screenshots in SRS |  |  | Completed
U3-04 | Phase 3 | Section 2 | Connect the Flutter application to Supabase: authentication, role-based access and the main required functions (e.g. attendance, announcements, notifications) | Group |  |  | Completed | 100 | Flutter app running against shared Supabase backend; mobile/ folder commits |  |  | Completed
U3-05 | Phase 3 | Section 3 | Develop the ASP.NET web application: main approved pages, navigation, forms and input validation based on the Figma web design | Group |  |  | Completed | 100 | Source code in web/ folder on GitHub; web screenshots in SRS |  |  | Completed
U3-06 | Phase 3 | Section 3 | Connect the ASP.NET application to Supabase: authentication, role-based access and the main required functions (e.g. marking attendance, posting announcements) | Group |  |  | Completed | 100 | ASP.NET app running against the same Supabase backend; web/ folder commits |  |  | Completed
U3-07 | Phase 3 | Section 4 | Shared process 1 - data submission and retrieval: attendance marked on the ASP.NET web application is saved to Supabase and retrieved on the Flutter mobile application | Group |  |  | Completed | 100 | Demonstrated web-to-mobile attendance flow; before/after screenshots in SRS |  |  | Completed
U3-08 | Phase 3 | Section 4 | Shared process 2 - shared update and display: an authorised update in one application (e.g. announcement or other approved record) is retrieved and displayed in the other application | Group |  |  | Completed | 100 | Demonstrated second shared process; screenshots in SRS |  |  | Completed
U3-09 | Phase 3 | Section 5 | Update the final SRS (single PDF): add Implementation and Final Prototype section with component overview, requirements-to-function table (working/incomplete), screenshots, approved changes, limitations, GitHub link and final Microsoft Project screenshot | Group |  |  | Completed | 100 | Updated BRIGHT_WEB_CRAFTERS_SRS.pdf (Phase 3 section in progress) |  |  | Completed
U3-10 | Phase 3 | Section 6 | Organise GitHub repository (mobile/ and web/ folders, README with setup/run instructions, backend schema scripts) and prepare final source-code ZIP matching the demonstrated version; confirm no passwords or secret keys are included | Group |  |  | Completed | 100 | GitHub repository link; ZIP 'Group [Letter] Phase 3' |  |  | Completed
U3-11 | Phase 3 | Section 6 | Update the Microsoft Project file with actual progress, responsibilities, completed development work and remaining tasks; capture final schedule screenshot for the SRS | Group |  |  | Completed | 100 | Updated editable .mpp file; schedule screenshot in SRS |  |  | Completed
U3-12 | Phase 3 | Section 6 | Update the ITC327W Project Progress Tracker: Task Progress, Individual Contributions, Challenges & Actions, Phase Summary and Phase 3 Group Reflection | Group |  |  | Completed | 100 | ITC327W_Project_Progress_Tracker_2026.xlsx (this workbook) |  |  | Completed
U3-13 | Phase 3 | Section 7 | Prepare the final presentation and live demonstration: stakeholder problem and solution, Supabase backend, mobile demo, web demo, two shared processes, limitations; all members rehearsed for questions | Group |  |  | Completed | 100 | Presentation slides and demo script; dummy data prepared |  |  | Completed
U3-14 | Phase 3 | Section 8 | Submit the group ZIP on Blackboard (one member), and each member completes the confidential individual contribution check | Group |  |  | Completed | 100 |  |  |  | Completed
Formulas:
Progress Flag = IF([Task Description]="","",IF([Status]="Completed","Completed",IF([Status]="Blocked","Blocked",IF([Status]="Delayed","Delayed",IF(AND([Due Date]<>"",[Due Date]<TODAY(),[Status]<>"Completed"),"Overdue","On Track")))))

## Individual Contributions
Individual Contribution Record
Student Name | Student Number | Reporting Phase | Activity | Assigned Responsibility | Work Personally Completed | Date Completed | Hours Spent | Evidence / Link | Verified by Group | Verification Date | Notes
LP Moshoeu | 223046876 | Phase 2 | Activity 3.3 | Figma(Mobile Application) | Do The figma mobile application | 25/09/2026 | 130 | https://www.figma.com/proto/pG7mL3Oj2Rr37JAT9r7WJv/School-Parental-system?node-id=42-238&p=f&t=0WVSbhhXYOH6dG98-1&scaling=scale-down&content-scaling=fixed&page-id=0%3A1&starting-point-node-id=42%3A238 | Yes | 25/09/2026
A Sithole | 223000460 | Phase 2 | Activity 3.3 | Figma(Web) | To do the figma web | 25/09/2026 | 132 | https://www.figma.com/proto/lPObV3qt8TfARP7lGBJZqU/School-Parental-System?node-id=197-2563&p=f&viewport=-167%2C288%2C0.1&t=Gi9OyypmECYmlsAf-1&scaling=contain&content-scaling=fixed&starting-point-node-id=197%3A2563&page-id=0%3A1 , https://www.figma.com/proto/lPObV3qt8TfARP7lGBJZqU/School-Parental-System?node-id=224-463&p=f&viewport=-107%2C84%2C0.19&t=7iRvLo52rvJGZx2o-1&scaling=contain&content-scaling=fixed&page-id=218%3A2&starting-point-node-id=281%3A2266 | Yes | 25/09/2026
MA Nkuna | 224000274 | Phase 2 | Activity 3.2 | ERD | To make our ERD | 25/09/2026 | 62 |  | Yes | 25/09/2026
ST Pheko | 223050336 | Phase 2 | Activity 3.1 | System Architecture | To make the system Archicture | 25/09/2026 | 60 | https://viewer.diagrams.net/?tags=%7B%7D&lightbox=1&highlight=0000ff&edit=_blank&layers=1&nav=1&dark=auto#Uhttps%3A%2F%2Fdrive.google.com%2Fuc%3Fid%3D1ClYwvn3JjYWEF-mdmsHK64CJf6675N-G%26export%3Ddownload | Yes | 25/09/2026
TMC Motone | 224027806 | Phase 2 | Activity 3.2 | Sequence Diagram | To draw up our Sequence Diagram | 25/09/2026 | 55 |  | Yes | 25/09/2026
PA Luthanda | 222023335 | Phase 2 | Activity 3.2 | Use Case Diagram | To make our use case | 25/09/2026 | 53 | https://viewer.diagrams.net/?tags=%7B%7D&lightbox=1&highlight=0000ff&edit=_blank&layers=1&nav=1&dark=auto#R%3Cmxfile%3E%3Cdiagram%20name%3D%22Page-1%22%20id%3D%22tkUWnzN3mPbntrwzPGwB%22%3E7V3bkqM4Ev2aehwHAsTlscrV07MR3bG9XRszu4%2BUUdvM2OAF1W2%2BfiVA2Eq7bCwrsd3lio4ZI4MwR0c6mamUuPHGi9fPZbKcfS1SNr9xnfT1xru%2FcV0SOp74nyx5a0uI4zQl0zJL27JVwUP2N2sL1WlPWcoq7UReFHOeLfXCSZHnbMK1sqQsixf9tB%2FFXL%2FrMpmyjYKHSTLfLP0jS%2FmsKY2osyr%2FjWXTGYfPt0jUyW1BNUvS4mWtyPt0443LouDNp8XrmM0legqX5rpf3%2Fm2%2B2Ely3mfC5Ln32c%2F%2FvVHOA0S8s9oufj%2Bd%2FXply21tEUVf1MYlMVTnjJZjXPj3b3MMs4elslEfvsiml2UzfhiLo6I%2BNhc%2FZzMn9qr2wJWcva6dof2R35mxYLx8k2cMlvHMQ5a2F5WqFMFZVuPp45bcvntYdK2%2BbSrewWL%2BNAicwBKbh%2BURPsu5cenxfx2wotSYCEfOhNc%2BpI8svm3osp4VuTilMeC82KxdsLtPJvKL3gB0PxR5LztFCTehu7D05KVoug2XWS5EdQx3QA60nEOdZhJjIUz7YOzqEd0fmbAxO9smlW8huthMhOjiBFe4SYxiQ%2BI6dGBEAtwEUvSVFbVguWkCU%2BwMKMxwIxiYRbiYiYkkHF2KthcDwu2qKmXpRuCuYlj8VRO2I666CbeeXor5VocFUsmxsI7UaJGPoHTXZpUs1qDiI6%2FLk7il5Rv%2F1k%2F%2BK88GFF1eP%2B6%2FuX9mzp6zXh92Sj2aXvcXOnVd5fHq0vlwfqV31iZCZDFyNKUNU%2FHk3LK%2BP7Oq2llkCwkwea8rmb96B%2F5ZP6USmJ15VPtrPZoG6lKNk949qw33Dqrgh2saav7VmSimTvi%2BZB4DqiiIUF71bpdAiqi4Z6KGhw3KqpJ3D2jOa%2BVpWmF2CEasRVBNXLS3dTsOsMo9vT%2BEO3rD%2FLIkNb0IFp%2FeuWsfs5z4XUY6nRUFuyhvA4caATQYXndy2o117nnjL3Ip6l%2FSaN1FZpB5etY%2BmjGAfFxUWNpxjXbgPEkwwMuoAA4NPOAUIvDqOLuWRoIQayNwcGeQdjcPlBcvFAD4acZSHs5WSdy%2F9U4Yu7%2FE3JoACDaRYbjAi1OH6htaRYXvSXnFbKHBoMBFG0I3jXi2tSuNdyQ1SsYDDrXonp1EV80L4Ac4AX0FBv1dBcqNhHRmOIFgR2x8YJhxcbtFQM9jdg0v8mst2%2BJMitkVSVOpMtMiBY1dXuFALFBdv1tIP%2BbJZOZjFEjgUx1kAnktzWQPW8QLR%2FPsnk6gBZBGQ9cLHZ6vkUtUq1gX4t66op3WDjo7HQFWCA%2B6C69dYXsqQhZVzzkubW2N05Ub0y4DOsl%2BUQ2ZZKn4r%2Bfy0RO5btjrC4KzcUAbULYQ55Duq3n3XgjBYNF1UKChlc8CPtWgOF6dBA3NENF3diOFMRYUmDilpgG4nrKjn%2Fh7gw0NkJD2XFBRcoeGEh2%2FGFCEquO3zZX%2Flgt6%2FPRQxQgNhaiaY4%2FkILPk6pitYRXlXBi6pk5Xgw1lhIHbzCNcAEclyypEz86CA0gi3pABly4CMbD7eVjIYdjPzW9t8ZrvauK245va%2Fbpot7YkQ%2Br%2BKPk5VFwb%2FGYu8Sjd6zKyI2w4LY5habY%2FiHUXjXZz6H2YWTqZILZ3jAEvwVZ7ekgZv6GxK98zapuoElRpltMAUujMd09GhMXgm4v2RPZ62wtAOWnCySXRcnRgAsAcD6ajgXIyt9Qbg26gajmRWhUQ%2B7Jrd0%2BRcUL2ubEQ7Mt1Z2sSHeALt0yi0VT7yBSam5Xv4%2FJjo0vWtNBemwEu2pvTYfmpw%2FMT2RND5E9%2BInympI8F1ydsIW8jRvUjVotk1y7UfC%2FJ7leqrnLL1Vzm1v580rWNHZ7gvikmv%2FG9ZrpzKClza9NtUHHiEHkjcZYfkOIbBf83mbN%2FOQNFKGpQ9QrdCOeTz5v0k4dT8Spcsxspozb02T7wDnmRZam8kvZGJMsn35hP%2BQ9vFXJ9xaYuoiXxV9sXMzlhPZ9XuSsVgme8OSxvoUcopdyNKlRoHfin%2FTH5VhP7%2BXsDb0jq2PxT55e8nGRi6qTrH4%2BllT8hVX85t25b7qNaF0227caqER%2BfHirOFtYsebdYIMUINGNutCBQmIE6ZfnYSsYJWt9evyTTQyzNwyiUjFabyIu8qq3r0n5l%2BZWGmHWJ%2FgJDXqC5juSfjkvFnS8JdyGl26z6GeXohCugbLIA2TPruMBe24a59ro7zQ69E5DtPgHwc7%2B%2BFJM5W%2FIrci0wayRhzduWp2CdzcxXzn2rS12YNzdA3%2B73Xhzd3xbGldvX%2FoAvxlIog9btn%2FC1Z6KsFeNqKnvMyDOkWueTkM4sjVzEIFy3e4M3UIlQ8rBUclVmZyDUc69Uu4oyrkDMQ7Ye67n2mGcB6mLzjjv%2FBg3cnxfZ50Xxqfh3THL6L1t8e9LIqPvDJviTHyb%2BROd%2FBxJRwKouIVSh%2B7DsJrFcTydsHuncY4YG7ftVnLWdAz0JWERzKFEp2Ngk447k3fPgo0aE62sSRyKc54f6zIKs2T7cg6SN3aGnawjfmhTj3euY%2B3rrh7CC0yenh3ngFqaJn0RGHiHqzjQOWdzZzBv5w5KV85Z5Vy39dbR49zgfkdsk3PHaevKGnP1nWFCQ4fhg5ARJqtSUzKCQHoMd4nAJiO1GSLenbd9HQCP5Jxu6EWUGHLu1IYetRld7rIRrqTDIB3kiuka8tOTzma0j9pS3djTeOcGezZsRfaFL4yNxIErFi%2BHjjY3ygiujgci6UJfJ10XnLs80tkMMqvk6ivprqTbSTqbYb0uBezKOhTWwQ224OIRY7%2BWDM06m4G98KqviKQDW%2BeRyNjHiGBkb2jS2YzsuQik20YfKzE%2BS2vhsfKmBGrJ29oJ7RqRdzkZOTqTvHZeYkWYpsaBsxIGT8oKbEZqPiKh1dzCifkcAz77jrOTeBFIQKXOQfx3wngU6wasKB0ZDut%2B5I%2Fi9T%2B9ZhpEIxgKRe8Xrs1%2BgRDAtNcvnFEsLHitbwR7M9KOMTvORQJAZq1PopF3UCeAKuAY7oPmx7v5H56A%2F1ZTJy9IF%2Byogn8eFO8mG5W9HB02ylsjONyoFk7to9PZZjD249G5W9R6aj6Dd6qq97D2tloAn4kpn2Hwjgyd1hTYTN%2F8eIRWfvypTRAYz%2FAP4zNcG%2BQZj8965gFx4fp4dD7bjOadt72NwWeVEnxqPgNCqtcQGPI5Mg2r%2BOGelGl0OluNE541neXrOwMQw0b0Hs9k5I430mYOYjoB4ZrIN2V6oFsiG28VwGa61b3lPp4honTv1HQG4cCYHjZwAzvGNd0RHg7cZOPl9Oh8vgbEj%2FUVw%2FOgNJygdvdExIHxQfz4VMZ4BH6IP%2FDawND9MH3AkdMYuvGydxeAI6yX8Dz6RvTOCpl3%2B4YP%2BgY9zLCH5o4LGd23b1AQACIhfNc2et%2BwGhg%2Fa8seRx%2BC8%2BwCxw73xr4qBX2DeMqkH4zSVoPjKBsT9H4But2ucGGjOngJJKGHJbU4cFdol4yC1Z%2FxkK1NbgbAuBl8PZyaesLbnzNPpkPubQr34I7RXvJEQquZvrsGCjv7yHtuqA0I9Oz2ke%2FoeJkbyUPxMl49trGRfDBwZifyxqPf2TSrJDvc9TfUN6%2BMOubN1QbbUW7M7fQYH8RhWcidSVeYi2eefS1SJs%2F4Pw%3D%3D%3C%2Fdiagram%3E%3C%2Fmxfile%3E | Yes | 25/09/2026
LP Moshoeu | 223046876 | Phase 3 | Sections 1 & 2 | Flutter and supabase | Developing some functions of flutter and making sure its connected to our supabase and it communicates with our ASP.NET application | 25/10/2026 | 90 | Submitted our project | Yes
A Sithole | 223000460 | Phase 3 | Sections 1 & 3 | ASP.NET and supabase | Developing some functions of our ASP.NET application and makiing sure it communicates with our supabase and that when they mark attendence what ever the case may be it interlinks withour flutter | 25/10/2026 | 150 | Submitted our project | Yes
MA Nkuna | 224000274 | Phase 3 | Sections 1 & 3 | ASP.NET and supabase | Developing some functions of our ASP.NET application and makiing sure it communicates with our supabase and that when they mark attendence what ever the case may be it interlinks withour flutter | 25/10/2026 | 150 | Submitted our project | Yes
ST Pheko | 223050336 | Phase 3 | Sections 1 & 2 | Flutter and supabase | Developing some functions of flutter and making sure its connected to our supabase and it communicates with our ASP.NET application | 25/10/2026 | 83 | Submitted our project | Yes
TMC Motone | 224027806 | Phase 3 | Sections 1 & 3 | ASP.NET and supabase | Developing some functions of our ASP.NET application and makiing sure it communicates with our supabase and that when they mark attendence what ever the case may be it interlinks withour flutter | 25/10/2026 | 79 | Submitted our project | Yes
PA Luthanda | 222023335 | Phase 3 | Sections 1 & 2 | Flutter and supabase | Developing some functions of flutter and making sure its connected to our supabase and it communicates with our ASP.NET application | 25/10/2026 | 81 | Submitted our project | Yes

## Stakeholder Engagement
Stakeholder Engagement Record
Date | Reporting Phase | Type of Engagement | Purpose | Students Present | Stakeholder Present / Role | Main Findings | Action Required | Evidence / Link
| Unit 1 / Phase 1 | Meeting | Requirements-gathering interview for the School Portal System | Group | J.B Setlhare - Administrator, Reitzpark Primary School (since 2021) | School currently has no dedicated app for parent communication; relies on printed circulars, class WhatsApp groups and Facebook; admin cannot confirm whether parents received/read notices. | Incorporate communication read/acknowledgement tracking into SRS requirements | Signed interview form, school-stamped (Reitzpark Primary School)
| Unit 1 / Phase 1 | Meeting | Requirements-gathering interview for the School Portal System | Group | Z. Horn - Educator, Thabong primary school (10 years) | Many parents have no WhatsApp, Facebook, data or smartphones; notices sent via class WhatsApp groups and Facebook often go unanswered or use wrong contact numbers; teacher cannot confirm receipt. | Confirm need for multi-channel and offline-friendly communication design; capture as a business rule in the SRS | Signed interview form, school-stamped (Reitzpark Primary School)
| Unit 1 / Phase 1 | Meeting | Requirements-gathering interview for the School Portal System | Group | R.I Mocke - Remedial Education, Lenakeng High school (14 years) | Parent meetings, phone calls and letters sent home with learners are current methods; letters often are not handed to parents and parents do not answer calls from the school; requested access to the system from phone/laptop. | Include Parent Acknowledgement feature and multi-device (web/mobile) access in the SRS | Signed interview form, school-stamped (Reitzpark Primary School)
| Phase 2 | Site Visit | We went to present our Figma mobile application prototype and Website prototype to get approval | Group | J.B Setlhare - Administrator, Reitzpark Primary School (since 2021) | The teachers were worried that our mobile application might be just a bit difficult for some parents to navigate | We promised teachers that we will make a short video tutorial on how to navigate the mobile application app so that we make it easier for parents to grasp how it works | Signed interview form, school-stamped (Reitzpark Primary School)
| Phase 3 | Site Visit | We went to present our final project for both our ASP.NET application and flutter application and they where happy with our project | Group | MM Landman | the school admin was concerned that the system might be tricky to se but they also said with time they will get used to the system | We must make a video for the school so that they can find it more easier to use the system | Signed interview form, school-stamped (Reitzpark Primary School)

## Challenges & Actions
Challenges and Corrective Actions
Date Identified | Reporting Phase | Challenge | Effect on Progress | Corrective Action | Responsible Student | Target Date | Status
| Unit 1 / Phase 1 | Parents at Reitzpark Primary School often lack smartphones, data or social media accounts, limiting WhatsApp/Facebook-based communication. | Adds complexity to designing an inclusive, multi-channel communication module. | Documented multi-channel communication and notification requirements in SRS Sections 5.10 and 9.1-9.3. | Group |  | Resolved
| Unit 1 / Phase 1 | The school has no reliable way to confirm parents received important notices (circulars, WhatsApp messages). | Highlighted a core stakeholder problem that had to be reflected accurately in the requirements. | Added Parent Acknowledgement and Read/Unread Tracking requirements (SRS Section 5.10.4-5.10.5). | Group |  | Resolved
| Phase 2 | Some of the the teachers at the school didn’t like our design of our mobile application as they felt it might be complicated for some parents to use | We had to redesign our mobile application prototype to try and make it easier for some parents to be able to navigate the mobile application | Mobile design prototype was adjusted slightly as to make it esier for parents | Group | 25/09/2026 | Resolved
| Phase 2 | Coming up with ideas for our web and mobile figma prototypes | It made us take longer to design as it required a lot of brainstrtorming and planning | We made suggestions to what could be improved or adjusted as to make it more easier to to make the necessary changes and adjustments | Group | 20/09/2026 | Resolved
| Phase 3 | we found that most parents would like if they could also view their kids previous reports on the flutter mobile application | We needed to re code our reports page so that the parents don’t just access their kids current reports but also their past reports | We made the system to be able to show previous reports | group | 21/10/2026 | Resolved

## Phase Summary
Phase Progress Summary
Summary Information | Group Response | Phase Completion Checklist
Reporting phase | Phase 3 | Initial or updated SRS completed | Yes
Reporting period |  | Progress report updated | Yes
Overall phase status | Completed | Individual contributions recorded | Yes
What was completed during this phase? | Completed our project build of flutter and ASP.NET | Stakeholder engagement recorded | Yes
What remains incomplete? | nothing | Challenges and actions updated | Yes
Why is it incomplete? | nothing | Group reflection completed | Yes
Which contributions were particularly important? | The stakeholder interviews with Reitzpark Primary School staff were particularly important, directly shaping the communication | Microsoft Project updated | Yes
Were there participation concerns? | yes | GitHub evidence available | Yes
What will the group improve in the next phase? |  | Confidential peer check completed | Yes
Main priority for the next phase

## Group Reflection
Group Reflection
Reflection Information | Group Response | Reflection Guidance
Reporting phase | Phase 3 | Length | Approximately 300–400 words in total.
Project title | School Portal System (School-Parental System) - ITC327W | Focus | Discuss the group’s actual experience, not the activity instructions.
Most important learning from this phase | Being able to think outside the box and finding ways to be more creative and adapt according to what will make our stakeholders satisfied | Honesty | Identifying a genuine challenge will not disadvantage the group when an improvement action is provided.
What went well and why? | setting up supabase as we had a clear uml diagram that guided us in ensuring we have everything necessary | Evidence | Ensure that claims about participation agree with the contribution record, Microsoft Project and GitHub.
What was difficult and why? | Brainstorming and coming up with ideas to make our website more attractive and pleasing to the eye | Research use | Student work may only be used for research after the required ethical approval and consent processes.
How were tasks divided among members? | 3 Members of the group did ASP.NET while the other 3 dealt with ASP.net
Did all members contribute fairly? Explain. | yes as each person did the task they were given
How did the group handle disagreements or delays? | We would have a group meeting to discuss whatever disagreement we had at the time
What did the group learn from the stakeholder? | The group learned that Reitzpark Primary School relies heavily on WhatsApp, Facebook and printed circulars to reach parents, but has no reliable way to confirm a notice was received or read, and that many parents lack smartphones or data. This directly informed the Parent Acknowledgement and Read/Unread Tracking requirements in the SRS.
Improvement action 1 for the next phase | Communication should be on point and we must communicate more and work according to our planned schedule
Improvement action 2 for the next phase
Priority for the next phase